## How it works
Risk based matrix - how it works
The good estate management for schools (GEMS) guidance sets out the principles of maintenance planning.
You should also read the GEMS guidance and the further information about prioritising maintenance before using this tool.
This tool will help you develop a risk based approach to prioritising maintenance to make best use of your resources. To do this, you will need to assess the condition of your estate along with risks and other factors that you consider important.
How to use the risk based matrix We have included some example maintenance activity in the workbook. These are only examples and are not intended to describe the risk associated with particular maintenance. You should consider and assess the severity of the risk in terms of the consequences for your organisation. This methodology can be adapted to meet your own needs. Please enter information into the cells shaded in grey. Once you have entered the risk data, the priority columns will change colour. This is to help you identify which works need prioritisation first.
Methodology This matrix is based on as assessment of risk factors and their severity and the probability of failure. The risk factors in the matrix cover: • health and safety and statutory compliance • the impact on the operation of the school • the potential financial or reputational implications • the impact on the ongoing condition of the building or elements within it. You could consider other risk factors to reflect your organisation's priorities. The probability of failure in the matrix is defined as: • unlikely • possible • likely • certain You will need advice from your building professional or use your condition surveys to help identify the probability of failure.
This is an example only and is not intended to provide a prescriptive methodology. You should use a methodology that suits the needs of your school or organisation. This methodology can be adapted to meet your own needs.
By applying a consistent methodology, you will be able to rank different maintenance works against each other and ensure that you focus and prioritise your resources to minimise risks.

## Risk based matrix
Risk based matrix
Before you start please read the accompanying document and 'how it works' tab
This matrix is based on as assessment of risk factors and their severity and the probability of failure. You can use the matrix to consider the risk factors and probability of failure of items if you don’t undertake the works, and rank them in order of priority. The simple numerical ranking can be used alone, or you could combine it with a simple colour ranking (red-amber-green approach).
Description |  |  | Risk Areas | [11 empty] | Severity of Risk |  | Likelihood of Failure |  |  | Priority |  | Decision
Ref | Location | Maintenance activity | Health and safety/statutory compliance |  | Score | Operational/service interruption |  |  | Maintenance budget/business/financial |  |  | Building or elemental condition/deterioration |  |  | Overall severity score | Value | Likelihood Score | Value | Description | Numerical Rating | Category | Outcome/next steps | Reasoning for decision | Estimated cost | Timeframe | Comments
1 | Main building | Boiler replacement | Minor | Minor injury, trivial breach of procedures or minimal breach of legal requirements | 2 | Major | Major impact and disruption to whole school operation | 4 | Major | Major impact on reactive maintenance budget, loss of reputation, financial penalty | 4 | Moderate | Will result in significant deterioration of building fabric or services if delayed | 3 | Moderate | 3 | Likely | 3 | Signs of significant deterioration/damage. Estimated time to failure within a year. | 9 | Resource Dependent
2 |  |  | Insignificant | No risk of injury or breach of procedures |  | Moderate | Impact on large part of school, disruption to normal school operation |  | Major | Major impact on reactive maintenance budget, loss of reputation, financial penalty |  | Insignificant | Work can be delayed without affecting condition of building or services |  | Minor | 2 | Likely
3 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  | Please select
4 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  | Please select
5 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please select
6 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
7 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
8 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
9 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
10 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
11 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
12 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
13 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
14 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
15 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
16 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
17 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
18 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
19 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
20 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
21 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
22 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
23 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
24 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
25 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select
26 |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please select |  |  | Please Select |  | Please Select

## Risk Categories
Severity of Consequences
Please select
Insignificant
Minor
Moderate
Major
Catastrophic
Probability of Failure
Please select
1 | Unlikely | Operationally sound. Normal wear and tear. Estimated time to failure 5-10 years.
2 | Possible | Some signs of minor deterioration/ damage. Estimated time to failure up to 5 years
3 | Likely | Signs of significant deterioration/damage. Estimated time to failure within a year.
4 | Certain | Failure imminent or has already occurred.
Probability of failure
[8 empty] | 1 | 2 | 3 | 4
| Severity |  |  | Health and safety/statutory compliance | Operational/service interruption | Maintenance budget/business/financial | Building or elemental condition/deterioration | Unlikely | Possible | Likely | Certain
Please select
Severity of consequences | 1 | Insignificant | 1 | No risk of injury or breach of procedures | Minimal or no impact on school operation | Minimal or no impact on reactive maintenance budget or reputation | Work can be delayed without affecting condition of building or services | 1 | 2 | 3 | 4
| 2 | Minor | 2 | Minor injury, trivial breach of procedures or minimal breach of legal requirements | Localised impact, little disruption or impact on school operation | Possible impact on reactive maintenance budget, complaint or impact on reputation | Could develop into minor deterioration of building or services if delayed | 2 | 4 | 6 | 8
| 3 | Moderate | 3 | Injury or illness resulting in absence, significant breach of procedures or legal requirements | Impact on large part of school, disruption to normal school operation | Significant impact on reactive maintenance budget, reputational impact, financial penalty | Will result in significant deterioration of building fabric or services if delayed | 3 | 6 | 9 | 12
| 4 | Major | 4 | Major injury, notifiable breach of legal requirements or procedures, litigation likely | Major impact and disruption to whole school operation | Major impact on reactive maintenance budget, loss of reputation, financial penalty | Serious deterioration of building and services and drop in overall condition category if delayed | 4 | 8 | 12 | 16
| 5 | Catastrophic | 5 | Fatality, prosecution from legal breach | Failure results in closure of whole school operation | Extensive impact on maintenance or capital budgets, reputational impact, significant financial penalties | Will result in complete building failure, unsuitable for occupation if delayed | 5 | 10 | 15 | 20
Please select